# ADO Task Breakdown — Instantly Shareable Playtest

Companion to SPEC.md and ARCHITECTURE.md. Every task is sized ≤ 5 days. Larger spec items (XC3 = 7d, PT6 = 5d but fan-out heavy) are split into independently assignable tasks. SWAGs are intentional “stupid wild *** guesses” — they exist to baseline capacity & timeline, not to be a commitment.

## Conventions

- ID — stable string used in references (PT1.a, XC3.b, …). The leading segment (PT1, XC3) maps to the deliverable in SPEC.md §4.

- Type — Epic / Feature / Task. ADO hierarchy: Epic → Feature → Task.

- Owner — the role / area that should pick this up. Names to be filled in once intern↔mentor pairings are set.

- SWAG — best-guess working days (one engineer, focused). Includes design, implementation, tests, code review wait. Does not include cross-team review SLAs that gate merge (those are tracked as dependencies).

- Depends on — must be merged before this task can start. Sibling tasks inside the same feature are otherwise parallelizable.

- Acceptance — concrete checkable criteria.

## Milestone-1 demo task (standalone)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| M1.demo | Foundational-demo harness: manual offering + Partner Center group flip | xCloud dev (with xPlaytest pair) | 2 | XC4.a, XC4.b, XC5.a | Operator script (PowerShell or a small console app) that (a) creates a new test offering via Partner Registry write path with one AllowedDnaGroups GUID; (b) attaches a known-good test title to it; (c) returns the launch URL. Manual test pass: a tester whose DNA-group membership is changed in Partner Center sees the offering become accessible / inaccessible within the GsToken refresh window. Validates the entire auth model end-to-end before any ingestion plumbing exists (SPEC.md §11 Milestone 1). |

## Epic

| ID | Title | SWAG (days) |
| --- | --- | --- |
| EPIC | Instantly Shareable Playtest — streaming opt-in for xPlaytest via xCloud | 54 dev-days across 2 teams (xCloud core 27 + M1.demo 2 + xPlaytest 25 = 54) |

The Epic is delivered across 5 milestones (SPEC.md §11) and 4 phases (SPEC.md §4.3). Phase A and B contain the foundational demo (Milestone 1) and the first end-to-end ingestion (Milestone 2) respectively.

## Features (rolling up the deliverables)

| ID | Feature | Team | Rolls up | SWAG |
| --- | --- | --- | --- | --- |
| F-XCLOUD-PR | xCloud — Partner Registry offering shape supports DNA-group gating | services.partnerregistry | XC4 | 5 |
| F-XCLOUD-AUTH | xCloud — User auth path enforces DNA-group membership | streaming-token / Bayside | XC5 | 5 |
| F-XCLOUD-SAGE | xCloud — SAGE exposes playtest ingestion routes to xPlaytest | services.serviceapigateway | XC1, XC2 | 4 |
| F-XCLOUD-CI | xCloud — Content Ingestion runs the PlaytestTitleIngestionWorkflow | services.contentingestion | XC3 | 9 |
| F-XCLOUD-INSTALL | xCloud — Install pipeline tolerates DNA-group as flight id + PC fork | install / SUCU | XC6 | 4 |
| F-XPT-CONTRACT | xPlaytest — Build the StoreAsset + ingestion payload | Xbox.Xbet.Service | PT2, PT3 | 5 |
| F-XPT-WORKFLOW | xPlaytest — Workflow integration + status polling | Xbox.Xbet.Service | PT1, PT4, PT5 | 15 |
| F-XPT-LIFECYCLE | xPlaytest — Lifecycle propagation (republish, audience, delete) | Xbox.Xbet.Service | PT6 | 5 |

## Tasks (≤ 5 days each)

### F-XCLOUD-PR — Partner Registry shape (XC4)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| XC4.a | Extend PlayerAuthorizationOptions schema | partner-registry dev | 2 | — | AllowedDnaGroups: List<Guid> and AllowedSandboxId: string added to PlayerAuthorizationOptions. JSON schema in Schemas/ updated. Existing OfferingV2 documents continue to deserialize (backfill on read: missing fields → empty list / "RETAIL"). Round-trip serialization test added. |
| XC4.b | Bulk-edit support for two-write playtest upsert + content-ingestion SPN allow-list | partner-registry dev | 2 | XC4.a | RegistryProvider.BulkEditAsync exposes a path that combines (create offering, attach title) into one PR to satisfy SFI manual-approval policy (SPEC.md §3.10). Unit test confirms a single commit / single PR is produced when both edits are queued together. Additionally, the services.contentingestion service identity is added to Partner Registry’s write-route allow-list (per ARCHITECTURE.md §3.4 item 5). Verified by integration test from content-ingestion INT. |
| XC4.c | OfferingV2.ToShortId() helper (≤ 32 chars) | partner-registry dev | 1 | XC4.a | New static helper produces a deterministic ≤ 32-char id from an input GUID (e.g., 12-hex-char prefix). Collision probability documented. Used by the workflow’s xpt-{shortId} derivation. Unit tests cover round-trip + collision behaviour. |

Feature SWAG total: 5 days. XC4.a is the critical sub-task for Milestone 1.

### F-XCLOUD-AUTH — DNA-group enforcement (XC5)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| XC5.a | Streaming-token DNA-group intersection check | streaming-token dev | 3 | XC4.a (schema only) | At offering-entry the streaming-token / Bayside path checks GsToken.DnaGroups ∩ offering.PlayerAuthorizationOptions.AllowedDnaGroups ≠ ∅. If empty → 403 with no playtest metadata in the response. Integration test verifies allow + deny paths. |
| XC5.b | Per-title entitlement bypass for playtest offerings | streaming-token dev | 1 | XC5.a | When the offering’s Title.IsPlaytest flag is set, skip the existing per-title entitlement check (since playtest titles have no Store entitlement). Behind a feature flag for safe rollout. Test covers both flag states. |
| XC5.c | Telemetry + denial reason codes | streaming-token dev | 1 | XC5.a | Denial emits Reason=PlaytestNotInDnaGroup for diagnosability without leaking offering metadata. Counter dashboard widget added. |

Feature SWAG total: 5 days. Required for Milestone 1.

### F-XCLOUD-SAGE — SAGE routes (XC1 + XC2)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| XC2.a | Allow-list Playtest Service SPN cross-tenant | SAGE dev | 1 | Lakshmi PR #15715445 merged | appsettings.xcloud.json has UseCrossTenantAuth: true and the xPlaytest SPN added to AuthorizedClientAppIds for the three new routes. Deployment to INT verified. |
| XC1.a | Add POST /playtest/ingestion route | SAGE dev | 1 | XC2.a, XC3.a (downstream contract stable) | Config-only addition forwarding to services.contentingestion’s POST /v3/workflows/playtestingestion. Response bodies forwarded unchanged (do NOT strip into x-Proxy-Error). Smoke test from a test SPN succeeds. |
| XC1.b | Add GET /playtest/ingestion/{jobId} route | SAGE dev | 1 | XC2.a, XC3.c | Config-only. Same forwarding behaviour, forwarding to GET /v3/workflows/playtestingestion/{jobId}. Smoke test polls and reads JSON status. |
| XC1.c | Add DELETE /playtest/ingestion/by-playtest/{playtestId} route | SAGE dev | 1 | XC2.a, XC3.d | Config-only. Forwards to DELETE /v3/workflows/playtestingestion/by-playtest/{playtestId}. Smoke test deletes a test playtest and verifies tombstone response. |

Feature SWAG total: 4 days.

### F-XCLOUD-CI — PlaytestTitleIngestionWorkflow (XC3 — split)

XC3 is the largest single piece. Split into four sub-tasks.

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| XC3.a | Define PlaytestIngestionJobParameters contract + controller route | content-ingestion dev | 2 | XC4.a | New DTO in the public contracts assembly matching openapi/playtest-ingestion.yaml. New route WorkflowsControllerV3.PlaytestIngestion accepts the payload, validates, schedules the workflow, returns 202 with jobId. 409 returns a JobConflict-shape body with the in-flight jobId and statusUrl when a non-terminal job already exists for the same playtestId. |
| XC3.b | Implement workflow state machine | content-ingestion dev | 5 | XC3.a, XC4.b, XC4.c, content-ingestion service identity allow-listed on Partner Registry write routes (per ARCHITECTURE.md §3.4 item 5) | New sealed PlaytestTitleIngestionWorkflow with stages: validate → schedule asset ingestion → poll asset ingestion → upsert offering (bulk-edit) → attach title → poll install readiness → emit terminal state. Reuses existing retry + idempotency patterns from TitleIngestionWorker. State transitions emit telemetry events. Unit tests cover happy path + each failure branch. Integration test confirms a published playtest with a slow asset ingestion (> 60 min) still reaches Streamable. |
| XC3.c | GET /v3/workflows/playtestingestion/{jobId} polling endpoint | content-ingestion dev | 1 | XC3.b | Returns current JobStatus. Terminal states populate terminalState, offeringId, titleId, errors[] per the OpenAPI schema. 404 for unknown jobId. Integration test verifies all four terminal states (Streamable, Failed, InstallNotFound, plus Running while in flight). |
| XC3.d | DELETE /v3/workflows/playtestingestion/by-playtest/{playtestId} tombstone endpoint | content-ingestion dev | 1 | XC3.b, XC4.b | New route sets offering.PlayerAuthorizationOptions.AllowedDnaGroups = [] via the bulk-edit path, schedules a GC pass for 7 days out. Idempotent. Returns 200 with { playtestId, offeringId, tombstoneTime }. 404 if no offering for playtestId. Integration test confirms subsequent stream attempts denied by XC5. |

Feature SWAG total: 9 days.

### F-XCLOUD-INSTALL — DNA-group as flight id (XC6)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| XC6.a | Audit install pipeline tolerance for non-GA flight id + PC fork | install dev | 2 | XC3.b (something to test against) | Documented walk of TitleIngestionWorker.cs:197-225 and SUCU client confirms (a) the path tolerates a non-GA flight id, and (b) the PC code path for ServerType + pool id (today the code hardcodes ServerType.XboxV3SeriesS and XBOX_* pools — see SPEC.md §3.6 risk callout). Audit posted as ADO comment. If a PC server type / pool id exists in the allocator client today, document its values; if not, file a follow-up task for the PC pipeline owner. |
| XC6.b | Wire deterministic “smallest GUID” selection + platform-aware filter | install dev | 2 | XC6.a | When resolving package version for a playtest title, pick the lexicographically smallest GUID of the current AllowedDnaGroups set at resolve time as the flight identifier (per SPEC.md §3.3). Branch the ServerFilter build on Platform so PC playtests pick the PC pool id + PC ServerType (audit findings from XC6.a). Behind feature flag. Unit + integration tests confirm: (a) same AllowedDnaGroups set always resolves to the same flight id, and therefore the same package version (deterministic); (b) adding a GUID that sorts higher than the current smallest does not change the selected flight id or resolved package; (c) adding a GUID that sorts lower than the current smallest does flip the selection — this is acceptable v1 behavior because flights are addressable by GUID alone and there is no notion of “first-chosen flight,” but the flip emits a XCloudFlightSelectionFlipped telemetry event with both old and new GUIDs so the install team can detect churn; (d) removing the previously-smallest GUID flips selection to the next-smallest and likewise emits telemetry; (e) a PC playtest does not hit Xbox-only allocator parameters (no ServerType.XboxV3SeriesS or XBOX_* pool ids on the resolved request). Design note: a sticky “first-chosen flight” model was considered but rejected for v1 because it requires extra per-playtest state in the install pipeline that doesn’t exist today — see SPEC.md §3.3. |

Feature SWAG total: 4 days.

### F-XPT-CONTRACT — StoreAsset & offering payload (PT2 + PT3)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| PT2.a | XboxTitleId resolver from XProduct | xPlaytest dev | 3 | — | New service that reads alternateIds[XboxTitleId] from the XProduct response and surfaces it on PlaytestProductDocumentBuilder. Replaces the current XboxLiveTitleId = string.Empty hardcode at PlaytestProductDocumentBuilder.cs:53-70. Validator now passes a non-zero XboxTitleId for a PC game. P0 blocker — must land before XC3.b can be integration-tested end-to-end. |
| PT2.b | AumID default-or-resolver | xPlaytest dev | 1 | — | For v1, a constant default "{packageFamilyName}!App" is acceptable (server-side use is telemetry-only per Timi). Document this in code comments and link to SPEC.md §3.6 / §5.2. v1.1 task tracked separately to plumb the real ApplicationId from the AppX manifest. |
| PT3.a | Package allowed-audience DNA groups into payload | xPlaytest dev | 1 | — | PlaytestPublishJobParameters.FlightIds (already GMS-resolved DNA group GUIDs) flow into PlaytestIngestionJobParameters.AllowedDnaGroups. Unit test asserts pass-through. |

Feature SWAG total: 5 days. PT2.a + PT3.a are independent and can run in parallel with PT2.b.

### F-XPT-WORKFLOW — Workflow integration + send + poll (PT1 + PT4 + PT5)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| PT1.a | Insert XCloudIngestionTriggerState into XPackagePlaytestPublishWorkflow | xPlaytest dev | 3 | PT2.a, PT2.b, PT3.a | New state inserted between PlaytestProductCreation and SuccessCompletion. Gated on IsStreamingEnabled flag (false by default). Failure of the new state does NOT block publish — it logs + emits telemetry. Workflow unit tests cover both flag states + xCloud-down failure. |
| PT1.b | Add IsStreamingEnabled opt-in field + streaming-expiration validation to publish request | xPlaytest dev | 1 | — | New boolean IsStreamingEnabled on the publish API surface, defaulting to false. When true, validate that PlaytestEndDate is non-null and in the future, returning 400 with a clear message otherwise (SPEC.md §9 Q3 + §7 blocker row). Documented in the public Playtest API contract. Unit tests cover both flag states and the new validation. |
| PT1.c | Seller / title allow-list gate for streaming publish | xPlaytest dev | 2 | PT1.b | New publish-side validator: when IsStreamingEnabled = true, reject publish unless the publisher’s SellerId (and optionally ProductId) is on a configurable allow-list. Allow-list is read from xPlaytest config (initially an in-config hardcoded list; future task tracks moving to a dynamic config service). Returns 403 StreamingNotEnabledForSeller with a clear error code. SPEC.md §10 P0 — “Creation of a private offering can be limited to a specific title / allow list of sellers.” Unit tests cover allowed-seller, denied-seller, allowed-seller + denied-title, and missing-config (fail-closed) cases. |
| PT4.a | XCloudIngestionClient (HTTP client) | xPlaytest dev | 2 | XC1.a, XC2.a | New typed HTTP client wrapping SAGE’s POST /playtest/ingestion. Cross-tenant S2S token acquisition. Returns (jobId, statusUrl). Polly-style retry on 5xx. Integration test against INT SAGE. |
| PT4.b | Persist jobId on PublishedPlaytestEntity | xPlaytest dev | 1 | PT4.a | Schema migration adds XCloudIngestionJobId, XCloudOfferingId, XCloudTitleId, XCloudStatus. Backfill = nullable. Persisted at end of PT1.a’s state. |
| PT5.a | Polling loop with exponential backoff | xPlaytest dev | 2 | XC1.b, XC3.c, PT4.b | Backoff per SPEC.md §3.1: 30s → 60s → 2min → 5min cap, 60min wall-clock. On terminal Streamable → set PlaytestStatus = StreamingReady + persist OfferingId / TitleId. On Failed / InstallNotFound → set StreamingFailed and persist error. Integration test asserts state transitions. |
| PT5.b | New StreamingReady value in PlaytestStatus enum + launch URL builder | xPlaytest dev | 1 | PT5.a | Enum value added (with migration safe-defaults). New BuildStreamingLaunchUrl(playtest) method on PlaytestBusinessLogic. Unit tests cover both. |
| PT5.c | Surface launch URL on Playtest GET API | xPlaytest dev | 1 | PT5.b | PlaytestResponse.StreamingLaunchUrl populated when status is StreamingReady. API contract bump (additive, non-breaking, still on v3). |
| PT5.d | Background reconciliation job for stuck ingestions | xPlaytest dev | 2 | PT5.a, PT4.b | New singleton timer service polls XCloudIngestionJobId from PublishedPlaytestEntity for any playtest stuck in WaitingForXCloud past the 60-min foreground deadline. Polls at 15-min intervals indefinitely up to 24 h, then alerts an on-call alias for manual triage (SPEC.md §3.1). On terminal state, transitions to StreamingReady / StreamingFailed exactly as PT5.a does. Integration test simulates a slow ingestion crossing the deadline and confirms eventual StreamingReady. |

Feature SWAG total: 15 days. PT1.c gates PT4.a (no point making the SAGE call if the publish is denied). PT4.* and PT5.* can pipeline against PT1.a once PT1.a is unblocked.

### F-XPT-LIFECYCLE — Lifecycle propagation (PT6 — split)

| ID | Title | Owner | SWAG | Depends on | Acceptance |
| --- | --- | --- | --- | --- | --- |
| PT6.a | Re-trigger ingestion on audience change | xPlaytest dev | 1 | PT1.a, PT4.a | Hook into PlaytestBusinessLogic.UpdatePlaytestAsync (PlaytestBusinessLogic.cs:408-553). On audience delta, re-call XCloudIngestionClient with the updated AllowedDnaGroups. xCloud’s idempotent upsert (keyed on playtestId) handles the update. Integration test: add tester, confirm new offering write within 60s. |
| PT6.b | Re-trigger on expiration change | xPlaytest dev | 1 | PT6.a | Same hook, expiry delta path. Integration test. |
| PT6.c | Re-trigger on build republish | xPlaytest dev | 2 | PT6.a, PT2.a | When a new package is uploaded, re-send StoreAsset with the new ContentId. xCloud upsert produces a new asset version under the same offering. Integration test: republish, confirm streaming session picks up the new build. |
| PT6.d | Teardown on playtest delete | xPlaytest dev | 1 | PT6.a, XC3.d, XC1.c | Wire into the existing delete workflow. Call DELETE /playtest/ingestion/by-playtest/{playtestId} on SAGE. Integration test: delete playtest, confirm tombstone response 200, confirm any subsequent stream attempt is denied by XC5. |

Feature SWAG total: 5 days.

## Roll-up

| Phase | Milestone | Tasks in scope | SWAG (days) |
| --- | --- | --- | --- |
| A | M1 — Foundational demo | XC4.a, XC4.b, XC4.c, XC5.a, XC5.b, XC5.c, XC2.a, PT3.a, M1.demo | 14 (parallel across teams) |
| B | M2 — End-to-end ingestion | XC3.a, XC3.b, XC3.c, XC3.d, XC1.a, XC1.b, XC1.c, XC6.a, XC6.b, PT2.a, PT2.b | 20 |
| C | M3 — xPlaytest integration | PT1.a, PT1.b, PT1.c, PT4.a, PT4.b, PT5.a, PT5.b, PT5.c, PT5.d | 15 |
| D | M4 — Lifecycle | PT6.a, PT6.b, PT6.c, PT6.d | 5 |
| — | M5 — Soak + handoff | (no new tasks; bug-fix + documentation) | 0 |

Grand total dev-days: ~54 days of focused work (xCloud core 27 + M1.demo 2 + xPlaytest 25 = 54), parallelizable across the 2 teams into roughly 7–8 calendar weeks with 1 engineer per team (matching the ~10-week internship including ramp + buffer).

SWAG accounting note (reconciles SPEC.md §4.2): SPEC.md lists xCloud feature subtotal = 27 and xPlaytest feature subtotal = 25 (after PT1.c). This roll-up adds M1.demo (2 days) to the xCloud column because the foundational demo is run primarily by the xCloud engineer. Cross-team totals therefore reconcile as xCloud (27 core + 2 demo) + xPlaytest 25 = 54.

## Cross-task notes for the ADO board

- Use tags: playtest-streaming, plus one of team:xpt or team:xcloud, plus the deliverable id (PT1, XC3, …).

- Use iteration paths aligned to milestones M1–M5.

- Acceptance criteria on each task should be copy-pasted into the ADO description so a reviewer can stamp by checking against them.

- Open Questions Q1, Q4, Q5 from SPEC.md §9 should be filed as discussion work items, not tasks (decisions, not deliverables), and stamped before M2 starts.