# Instantly Shareable Playtest

Spec at a glance — for reviewers

Melanie Chen · Microsoft Gaming Intern (Cloud Streaming)

Draft v1 — 2026

# Instantly Shareable Playtest

Owner: Melanie Chen (xPlaytest) Status: Spec v1 — ready for implementation Companion docs: SPEC.md (long form), ARCHITECTURE.md, openapi/playtest-ingestion.yaml, ado/ado-tasks.md

## 1. What we are building

Today xPlaytest distributes private pre-release builds to testers as downloadable installs. Modern games are hundreds of gigabytes — downloads are slow and hardware does not scale.

This project adds a streaming option. When a creator publishes a playtest with Enable Cloud Streaming checked, the build is ingested into xCloud and becomes streamable through a shareable link, in addition to the existing download flow. The behavior is purely additive: creators who opt out are unaffected.

## 2. End-to-end flow

| # | Phase | What happens | Owner |
| --- | --- | --- | --- |
| 1 | Publish | Creator hits Publish in Partner Center. The publish workflow runs as today and gains a new final state, XCloudIngestionTrigger. | xPlaytest |
| 2 | Handoff | The new state POSTs a PlaytestIngestionJobParameters payload to SAGE and stores the returned jobId. Failure is non-fatal — download still publishes. | xPlaytest → xCloud |
| 3 | Ingestion | A new PlaytestTitleIngestionWorkflow chains asset ingestion, creates a private offering xpt-{id}, attaches the title, and waits for install readiness. | xCloud |
| 4 | Streamable | xPlaytest polls SAGE for terminal state, sets PlaytestStatus = StreamingReady, and surfaces the launch URL. | xCloud → xPlaytest |

A code-grounded sequence diagram lives in ARCHITECTURE.md.

## 3. Design decisions

- Streaming is opt-in, additive to the download flow — keeps the existing creator path unaffected and the new path low-risk.

- One playtest = one title = one offering in v1. Each playtest targets a distinct audience, so the auth boundary stays 1:1. Clustering is a v1.1 concern.

- PC only in v1. The existing publish path already targets WINDOWS.DESKTOP; console support adds Xbox-only allocator and title-id handling and is deferred.

- Auth is gated at the offering level, not per title — one DNA-group check at offering entry, matching the pattern TestX already uses.

- Bespoke POST /playtest/ingestion rather than a generic CreateOfferingFromStoreData. Keeps the contract small and lets us encode playtest defaults (RETAIL sandbox, private audience) server-side. A generic surface is the future direction but out of summer scope.

- Polling for terminal state, not callbacks. SAGE is a request/response proxy today; cross-tenant callbacks need a message bus that does not yet exist. Polling reuses the publish workflow’s existing retry primitives.

- Install lookup uses a single flight id — the lex-smallest DNA-group GUID. The install pipeline only accepts one, and all groups in a playtest point to the same build, so the choice is deterministic and re-run-stable. The audience check (XC5) still evaluates the full set.

- Offering id is opaque (xpt-{shortId}) because it has a 32-char cap and is auth-critical. Title id is name-derived for readability — strip the playtest name to alphanumeric and append the product id for uniqueness.

- Short-term cross-tenant auth runs Green → Corp via SAGE, riding an in-flight PR. The long-term PME story is owned by the GSS platform team and is out of scope.

- Delete is a tombstone + 7-day GC, not a synchronous hard delete. SFI requires manual PR approval for Partner Registry writes, so a true hard delete is not achievable in v1. Tombstoning clears AllowedDnaGroups immediately so testers lose access, and the offering disappears from the DevApi listing. Needs explicit sign-off from xCloud reviewers.

- Streaming-enabled playtests must carry an explicit expiration. xCloud needs a bounded end date; download-only playtests are unaffected. UI default is 90 days with a soft warning above 180.

- Offering write + title attach are bundled into one PR — cuts the manual SFI approval cost in half (one PR per publish instead of two).

- External API is unversioned today; internal routes live under /v3/... to match existing SAGE and WorkflowsControllerV3 conventions. Future breaking changes bump to /v2/playtest/ingestion; additive optional fields do not require a bump.

## 4. Work breakdown

Full task-level breakdown with acceptance criteria is in ado/ado-tasks.md. The roll-up below uses SWAGs in developer-days.

### xPlaytest (25d)

| ID | Deliverable | SWAG |
| --- | --- | --- |
| PT1 | Insert XCloudIngestionTrigger state in XPackagePlaytestPublishWorkflow; add publish-time validators (streaming requires expiration; seller allow-list) | 6 |
| PT2 | Build StoreAsset from playtest product / package data; resolve XboxTitleId from XProduct alternateIds; ship AumID default | 4 |
| PT3 | Project resolved DNA-group IDs into the offering config | 1 |
| PT4 | New XCloudIngestionClient (cross-tenant S2S, retries, 202/409 handling, jobId persistence) | 3 |
| PT5 | Polling loop (exponential backoff) + background reconciliation job for slow ingestions; StreamingReady state + launch URL | 6 |
| PT6 | Lifecycle updates: audience / expiry change → re-trigger; delete → call DELETE …/by-playtest/{id} | 5 |

### xCloud (27d, plus 2d demo prep)

| ID | Service | Deliverable | SWAG |
| --- | --- | --- | --- |
| XC1 | SAGE | New routes: POST /playtest/ingestion, GET …/{jobId}, DELETE …/by-playtest/{id} | 3 |
| XC2 | SAGE | Allow-list the xPlaytest S2S identity (cross-tenant) | 1 |
| XC3 | services.contentingestion | PlaytestTitleIngestionWorkflow, contract types, controller routes | 9 |
| XC4 | services.partnerregistry | AllowedDnaGroups + AllowedSandboxId on OfferingV2; bulk-edit for offering + title in one PR | 5 |
| XC5 | User-login / offering auth | GsToken.DnaGroups check at offering entry; skip per-title entitlement for playtest titles | 5 |
| XC6 | Install pipeline | Pick lex-smallest flight id; branch ServerFilter so PC playtests skip the Xbox-only allocator parameters | 4 |

Execution order (2 devs in parallel):

Phase A (wk 1–2)   XC4, XC5, XC2, PT3       → no inter-dependencies
Phase B (wk 2–4)   XC1, XC3, XC6, PT2       → A must land first
Phase C (wk 4–6)   PT1, PT4, PT5            → B must land first
Phase D (wk 6–7)   PT6                      → C must land first
Soak  (wk 7–10)    end-to-end stabilization, OpenAPI publish, runbooks

## 5. Contracts

The external REST contract lives in openapi/playtest-ingestion.yaml. Internal contract types and code references live in ARCHITECTURE.md. Full rationale, alternatives, and code citations live in SPEC.md.

The central payload is PlaytestIngestionJobParameters. Required fields are PlaytestId, AllowedDnaGroups (min 1), ExpirationTime, and StoreAsset. AllowedSandboxId and IsGreenSigned are optional and default server-side to RETAIL and true. CallbackUrl and CorrelationId are reserved for future use.

## 6. Milestones

| # | Milestone | Target | Definition of done |
| --- | --- | --- | --- |
| M1 | Foundational demo — manual offering with a fixed DNA group; Partner Center group membership changes flip tester access live | end of wk 2 (≤ 6/20) | XC4 + XC5 shipped; operator script provable end-to-end |
| M2 | Ingestion — manual curl against SAGE drives the full ingestion to a streamable offering | end of wk 4 (≤ 6/30, Midpoint Connect) | XC1, XC2, XC3, XC6, PT2 shipped |
| M3 | xPlaytest integration — Publish in Partner Center end-to-end produces a launch URL | end of wk 6 (≤ 7/14) | PT1, PT4, PT5 shipped |
| M4 | Lifecycle — audience / expiry / republish / delete reflect in xCloud | end of wk 7 (≤ 7/21) | PT6 shipped |
| M5 | Soak + handoff — real studio build; OpenAPI + runbooks published | end of wk 10 (≤ 7/28, Final Connect) | End-to-end test passes; docs live |
| — | Presentation | wk 11–12 | Intern presentation |

## 7. Success criteria (P0)

A v1 release passes when all of the following hold:

- Publishing a streaming-enabled playtest submits the xCloud ingestion within seconds and becomes live within one approver round-trip.

- The offering exists in Partner Registry with the audience’s DNA groups and a non-null expiration.

- The offering contains exactly one title corresponding to the playtest.

- An authorized tester can stream the playtest through xCloud via the launch URL.

- An unauthorized user opening the launch URL is denied with no metadata leakage.

- Audience, expiration, and build-republish changes after publish all re-propagate to xCloud.

- Deleting the playtest removes tester access within the GsToken refresh window and removes the offering from DevApi.

- Streaming-enabled publish is gated behind a seller / title allow-list feature flag during private preview.

- xCloud ingestion failure does not block the download playtest from publishing.

P1 (deferred): Bayside login flow on the launch URL; GSSV /offerings returns the user’s accessible playtest offerings for in-client discovery. P3 (out of scope): Xbox console support, region / touch-control configuration, in-stream feedback collection.

## 8. Known risks and open items

- Cross-tenant S2S long-term (PME). Open. The GSS platform team owns the PME story. xPlaytest rides the short-term Green → Corp PR; the call site is marked for revisit.

- Manual PR approval on Partner Registry writes. Mitigated. One bundled PR per publish instead of two; xCloud reviewers approve out-of-band for the duration of the internship.

- XboxTitleId resolver. Open — P0 inside PT2. Read alternateIds[XboxTitleId] from XProduct; replaces today’s empty hardcode.

- AumID for PC. Decided. Ship a constant default for v1 (telemetry-only on the server side); v1.1 plumbs the real ApplicationId from the AppX manifest.

- PC install poll path. Open — audit lives in XC6. Today’s allocator parameters are Xbox-only. XC6 audits the path and branches ServerFilter on Platform.

- Stable playtest identity for offering id. Open. xPlaytest confirms whether PartnerCenterProductId is stable across republishes (the recommended option); otherwise we use the equivalent stable upstream id. This is the one open item that materially changes the offering-proliferation story on nightly republishes.

- Delete model (tombstone vs. hard delete). Decision pending sign-off. v1 ships tombstone + 7-day GC. User-visible behavior matches the P0 wording, but the deviation needs explicit xCloud sign-off.

## Glossary

- DNA group — GMS audience grouping; resolves to the GUIDs in AllowedDnaGroups.

- GMS — Group Management Service.

- GsToken — Game Streaming token; carries DnaGroups claims.

- SAGE — Service API Gateway; cross-tenant ingress proxy for xCloud.

- SUCU — Streaming Update Catalog; xCloud’s package-version resolution.

- SFI — Secure Future Initiative; the policy regime that forbids self-approving PRs.

- xpt-{id} — Offering id prefix for playtest-derived offerings.